## COMPLETE TASK BREAKDOWN - ALL PHASES

Stories Covered: 9 core modules | Timeline: 7-Day Sprint | Target Date: March 21, 2026

### MODULE 1: PROJECT INITIALIZATION & GITHUB SETUP

Focus: Repository Structure & CI/CD Foundation

Day: 1 (Early Morning)

| Task ID | Task Description | Role | Duration | Definition of Done |
| --- | --- | --- | --- | --- |
| INIT-01 | Create GitHub Repository social-recipe-app | DevOps | 0.5h | Repository created with initial README |
| INIT-02 | Setup Monorepo folders: /backend and /frontend | DevOps | 0.5h | Folder structure committed to main |
| INIT-03 | Initialize Spring Boot 3 Backend (Java 17/21) | Backend | 1h | Initial builds successfully in local env |
| INIT-04 | Initialize Vite + React 18 Frontend | Frontend | 1h | Default React page loads via Vite |
| INIT-05 | Create initial docker-compose.yml for PostgreSQL | DevOps | 2h |  |

### MODULE 2: AUTHENTICATION & USER BACKEND

Focus: Spring Security & User Identity

Day: 1

| Task ID | Task Description | Role | Duration | Definition of Done |
| --- | --- | --- | --- | --- |
| AUTH-BE-01 | Create User Entity (id, email, password, counts) | Backend | 2h | Entity class with JPA annotations created |
| AUTH-BE-02 | Configure Spring Security 6 with JWT | Backend | 4h | Unauthenticated requests return 401 |
| AUTH-BE-03 | Implement POST /api/auth/register and /login | Backend | 3h | JWT token returned upon valid login |
| AUTH-BE-04 | Implement Follow/Unfollow Logic | Backend | 3h | Follower/Following counts update in DB |
| AUTH-QA-01 | Write unit tests for JWT extraction | QA | 2h |  |

### MODULE 3: RECIPE CORE BACKEND

Focus: CRUD and Data Persistence

Day: 2

| Task ID | Task Description | Role | Duration | Definition of Done |
| --- | --- | --- | --- | --- |
| RCP-BE-01 | Create Recipe, Ingredient, and Step Entities | Backend | 3h | Bidirectional JPA relationships established |
| RCP-BE-02 | Implement POST /api/recipes (Recipe Creation) | Backend | 3h | Recipe saved with nested steps/ingredients |
| RCP-BE-03 | Integrate Cloudinary Signed URL Generator | Backend | 2h | Backend returns signature for secure upload |
| RCP-BE-04 | Implement GET /api/recipes/{id} Detail View | Backend | 2h | Returns full recipe JSON with author data |
| RCP-DB-01 | Setup Liquibase/Flyway for Recipe tables | Database | 2h |  |

### MODULE 4: SOCIAL FEATURES & SEARCH

Focus: Feeds, Comments, and Full-Text Search

Day: 3

| Task ID | Task Description | Role | Duration | Definition of Done |
| --- | --- | --- | --- | --- |
| SOC-BE-01 | Implement Like/Unlike with Atomic Upsert | Backend | 3h | Like count updates without race conditions |
| SOC-BE-02 | Create Comment Entity and Threaded API | Backend | 3h | Comments saved and retrieved for recipes |
| SOC-BE-03 | Implement Personalized Feed Query (Followed Users) | Backend | 3h | SQL query using IN (followed_ids) works |
| SOC-BE-04 | Setup PostgreSQL GIN Index for Search | Database | 2h | Search by ingredient name is performant |
| SOC-BE-05 | Implement Cursor-based Pagination for Feeds | Backend | 3h |  |

### MODULE 5: FRONTEND FOUNDATION & AUTH UI

Focus: React Setup & Infinite Scroll

Day: 4

| Task ID | Task Description | Role | Duration | Definition of Done |
| --- | --- | --- | --- | --- |
| FE-INIT-01 | Setup Tailwind CSS and Theme Config | Frontend | 2h | Global styles and colors applied |
| FE-AUTH-01 | Create Login/Register Forms (React Hook Form) | Frontend | 3h | Validation works; JWT stored in LocalStorage |
| FE-FEED-01 | Create Explore Feed with React Query | Frontend | 4h | Infinite scroll fetches next page on scroll |
| FE-COMP-01 | Design Recipe Card Component | Frontend | 2h |  |

### MODULE 6: CREATE RECIPE FLOW

Focus: Complex Forms & Cloudinary Upload

Day: 5

| Task ID | Task Description | Role | Duration | Definition of Done |
| --- | --- | --- | --- | --- |
| FE-RCP-01 | Build Multi-step Recipe Form | Frontend | 4h | User can navigate through form steps |
| FE-RCP-02 | Implement Dynamic Step/Ingredient addition | Frontend | 2h | "Add more" buttons work for lists |
| FE-RCP-03 | Setup Cloudinary Upload Widget + Preview | Frontend | 4h | Image preview shown before final submit |
| FE-RCP-04 | Handle Recipe Submission Payload | Frontend | 2h |  |

### MODULE 7: PROFILE & SOCIAL UI

Focus: Profile Pages & Interactions

Day: 6

| Task ID | Task Description | Role | Duration | Definition of Done |
| --- | --- | --- | --- | --- |
| FE-PROF-01 | Create User Profile Page | Frontend | 3h | Displays user bio and their recipes |
| FE-SOC-01 | Implement Follow/Unfollow Buttons | Frontend | 2h | UI toggles state and updates count via API |
| FE-SOC-02 | Add Comment Section to Recipe Detail | Frontend | 3h | Users can post and view comments |
| FE-SOC-03 | Create Liked Recipes Tab on Profile | Frontend | 2h |  |

### MODULE 8: POLISH, DOCKER & DOCUMENTATION

Focus: Deployment & Quality Assurance

Day: 7

| Task ID | Task Description | Role | Duration | Definition of Done |
| --- | --- | --- | --- | --- |
| DEPLOY-01 | Finalize Docker Compose (Frontend + Backend + DB) | DevOps | 4h | docker-compose up runs entire app |
| QA-01 | Implement Loading Skeletons for Feeds | Frontend | 2h | Smooth UI transitions during data fetch |
| QA-02 | End-to-End Testing (Search to Checkout) | QA | 4h | Full user journey verified manually |
| DOC-01 | Write Comprehensive README.md | Documentation | 2h |  |

### SUMMARY OF EFFORT

| Role | Total Estimated Hours | Percentage |
| --- | --- | --- |
| Backend Development | 35 Hours | 38% |
| Frontend Development | 38 Hours | 41% |
| Database/DevOps | 11 Hours | 12% |
| QA/Documentation | 8 Hours | 9% |
| TOTAL | 92 Hours | 100% |

### CCEPTANCE CRITERIA CHECKLIST

- [ ] Auth: All protected routes return 401 without a valid JWT.

- [ ] Cloudinary: Images upload directly from frontend via signed URLs.

- [ ] Feed: Infinite scroll works on both Explore and Personalized feeds.

- [ ] Search: Recipes are searchable by ingredient using GIN indexes.

- [ ] Social: Likes and Follows update counts immediately in the UI.

- [ ] Docker: App launches with a single command.